## Strategy
2008 | [5 empty] | 2009 | [11 empty] | 2010 | [11 empty] | 2011
Jul | Aug | 2008-09-01 | 2008-10-01 | 2008-11-01 | 2008-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01 | 2009-01-01 | 2009-02-01 | 2009-03-01 | 2009-04-01 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2009-12-01
Planning/Strategy | [6 empty] | Advising | [6 empty] | GPEM |  |  |  |  | Imagio |  | Advancement | [6 empty] | Athletics |  |  |  | TBD |  |  |  | TBD
|  |  |  | Sytem Config |  |  |  | Child Law |  | Ugrad | [5 empty] | A/P |  |  |  |  | MHC |  | HR | [5 empty] | Purchasing |  |  |  | TBD |  |  |  | TBD
|  |  |  | FA/Enrollment Ops |  |  |  |  | FA/En Ops |  |  | Support Services & Hubs | [6 empty] | Reg Rec |  |  |  | PV |  | Student Affairs |  |  |  |  | AA: Schools |  |  |  | TBD |  |  |  | TBD
[9 empty] | TBD |  | TBD |  | TBD |  | Bursar-Cd's |  | TBD |  |  | OIP |  |  |  | TBD |  | TBD | Finance |  |  |  | AA: Provost |  |  |  | TBD |  |  |  | TBD
Legend:
Phase I - Basic Imaging, Apples to Apples incl. low hanging fruit. | [12 empty] | Phase II - Advanced ECM - Workflow Etc. | [8 empty] | System Shutdown & Turnoff | [6 empty] | Product Tasks

## Value
| Intra Office |  |  | Inter Office |  |  | Broader Institutional Impact
Functional Areas Priority & Value Grid | Enhanced management of records/ paperwork | Process improvements & efficiencies | Increased records security & protection | Reduction in physical storage space requirements | Improved information collaboration & sharing | Common language & transferable skills | Support Green Initiatives | Annual operational savings
AA: Financial Aid/Enrollment Ops | E | I | E/X | E | X | X | X | X
AA: Advising - Central & Schools | T | T | X | X | X | X | X
AA: Academic Support Services & HUB | T | T | X | X | X | X | X
AA: Ugrad Admission | E | I | E/X | E | X | X | X | X
AA: GPEM | E | I | E/X | E | X | X | X | X
AA Schools: Law: Child Law Project | I |  | X | X | X | X | X
Finance: Accounts Payable | E/A | A | X | E | X | X | X | X
Finance: Bursar-CDs |  | I | E/X |  | X | X | X | X
AA: Office International Programs | T | T | X | X | X | X | X
AA: Registration & Records | E/T | T | E/X | X | X | X | X | X
Advancement | A | A | X | X | X | X | X
Human Resources | A | A | X | X | X | X | X
Student Affairs (SA) | I | I | X | X | X | X | X
Finance: Purchasing | I | I | X | X | X | X | X
Finance: Other | I | I | X | X | X | X | X
SA: Athletics | I | I | X | X | X | X | X
AA Schools: Other Projects | I | I | X | X | X | X | X
AA Provost: Other Projects | I | I | X | X | X | X | X
Value Indicators |  |  | Business Process Impact/Maturity
Existing value with current systems | E |  | Business Improvement |  | I
Extended/New value with ECM | X |  | Business Advancement |  | A
|  |  | Business Transformation |  | T

## Dependencies
Department | Timing | Timing to avoid | Timing (Dates to avoid)
Accounts Payable | Q2 - Q4 | Lawson upgrade - Feb 09 Audit - Mar - Sept(?) | AP - Lawson upgrade (Feb 09), Audit (Mar - Sept) | Purchasing - Lawson upgrade (Feb 09)
Advancement |  | October - calling programs | Advancement - October, plus campaigns | Reg & Rec - Start of school & registration periods
Athletics |  | August, start of school | Athletics - Aug, start of school | Student Affairs - start of school, move-in/move-out
Bursar | Feb, March, April, Sept, Oct, Nov, Dec | Start of semester (Aug / Jan) & registration periods | Bursar - start of semesters & registration periods | Support Services/Hubs - Start of semesters and reg.
Finance / Comptroller | Feb, Mar, Jun, Aug, Sept, Nov, Dec | Lawson upgrade - Feb 09 May and 1st of each qtr | Finance - Lawson upgrade (Fed 09), May and 1st mo of qtr | Ugrad / Advising - best time late spring / summer
GPEM | Oct / Nov - best time | No real timing cycle | GPEM - No real timing cycle | Child Law - No restrictions
Human Resources | Feb, Mar, Apr, May, Sept, Oct, | Summer, start of school, Lawson upgrade | HR - Lawson upgrade (Feb 09), summer, start of school | OIP - No real restrictions
OIP | No real restrictions
Purchasing | Any time | Lawson upgrade
Reg & Rec | Feb, March, April, Sept, Oct, Nov, Dec | Start of semester and registration periods
Student Affairs (Res Life) | Feb, Mar, Apr, Sept, Oct, | Start of semester, Move-in, Move-out / each semester
Student Services (Hubs) | Feb, March, April, Sept, Oct, Nov, Dec | Start of semester and registration periods
Ugrad w/ Advising & colleges | Admissions - Late spring / summer Advising - March / April (slowest period)
Child Law | ASAP

## Team
Team Composition
Needs Analysis Phase | Implementation - Phase | Academic Project Oversight | Non-Academic Project Oversight | Additional Roles
PM - Jim Sibenaller | PM - Ray Pauliks | John Pelissero | Susan Malisch | Process Analyst
Functional Leads: | Functional Leads: | AA ECM Oversight Comm. | ECM Oversight Comm. | Business Analyst
Tom Mathewson | TBD - Based on Area |  |  | Business Product Owner
Brian Slavinskas |  |  |  | Project Admin
Eric Pittenger | Tech. Product Ownership - Walt Slazyk | Project Review Board | Project Review Board | Program Owner
Imerge - Jim Just | ECM Analyst - Katherine Kim
Moran - Craig Foley
| Imerge - Jim Just | ITESC | ITESC
Security - Sean Smith